## SEP Gantt chart
| Colour coding: | Milestones |  | Assessments-See red tags
|  | Due dates |  |  | September |  |  |  |  | October | [30 empty] | November | [29 empty] | December | [30 empty] | January | [30 empty] | February | [27 empty] | March | [30 empty] | April | [29 empty] | May | [30 empty] | June
|  | Assessments |  |  | Week 1 | [6 empty] | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4 | [6 empty] | Week 5 | [6 empty] | Week 6 | [6 empty] | Week 7 | [6 empty] | Week 8 | [6 empty] | Week 9 | [6 empty] | Week 10 | [6 empty] | Week 11 | [6 empty] | Week 12 | [6 empty] | Winter vacation Wk 1 | [6 empty] | Winter vacation Wk 2 | [6 empty] | Winter vacation Wk 3 | [6 empty] | Assessments Wk 1 | [6 empty] | Assessments Wk 2 | [6 empty] | Week 13 | [6 empty] | Week 14 | [6 empty] | Week 15 | [6 empty] | Week 16 | [6 empty] | Week 17 | [6 empty] | Week 18 | [6 empty] | Week 19 | [6 empty] | Week 20 | [6 empty] | Week 21 | [6 empty] | Spring vacation Wk 1 | [6 empty] | Spring vacation Wk 2 | [6 empty] | Spring vacation Wk 3 | [6 empty] | Week 22 | [6 empty] | Week 23 | [6 empty] | Week 24 | [6 empty] | Week 25 (revision week) | [6 empty] | Assessments Week 1 | [6 empty] | Assessments Week 2 | [5 empty] | Assessments Week 3
|  | Unavailable |  |  | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3
Task Completed on this date
Task ID | Category | Task | Lead | Notes(is green when complete)
1.1 | Client liaison | Contact client to arrange first meeting | bar: Week 2 3
1.2 | Client liaison | Research client | ALL | bar: Week 2 3 to Week 2 4
1.3 | Client liaison | Plan agenda for first meeting and key questions to answer | bar: Week 2 3 to Week 2 4
1.4 | Client liaison | Take notes during meeting and send to all attendees
1.5 | Client liaison | Add client key dates to Gantt chart
2.1 | Project planning | Arrange time and place group will work together and how you will communicate | bar: Week 2 3
2.2 | Project planning | Arrange to meet your mentor | bar: Week 2 3
| Project planning | Add key dates to your Outlook calendars, Gantt Chart and project descriptions | See red tags and blue higlights |  | Week 2 6: intro to client; Week 11 9: p2p mvp; Week 12 13: Meeting with client; Week 14 30: Meeting with client; Week 19 8: Meeting with client; Week 21 22: p2p beta; Spring vacation Wk 2 4: Meeting with client; Week 23 28: Final Meeting
4.1 | Code evaluation | Remove redundant config file | bar: Week 4 18
6.1 | Documentation | Review and revise README | bar: Week 6 4
6.2 | Documentation | Meeting minutes | bar: Week 6 4
5.1 | Enhancement | Remove depreciated buttons | bar: Week 5 24
5.2 | Enhancement | Remove questions section | bar: Week 5 24
5.3 | Enhancement | Rename dashboard section as flashcard section | bar: Week 5 26
5.4 | New Feature | Added landing page | bar: Week 5 30
8.1 | New feature | Added New screen content | bar: Week 8 17
8.2 | New Feature | New dashboard screen text | bar: Week 8 17
8.3 | New Feature | Added setup guide | bar: Week 8 17
8.4 | Bug Fix | Fixed mark scheme | bar: Week 8 17
8.5 | Bug Fix | Landing page back arrow bug fixed | bar: Week 8 17
10.1 | Bug Fix | Logging out prevent navigation | bar: Week 10 2
W2.1 | Documentation | Added more user stories | bar: Winter vacation Wk 2 1
W3.1 | Bug Fix | Removed special characters | bar: Winter vacation Wk 3 2
9.1 | Enhancement | Change Text Height | bar: Week 9 27
W2.2 | CD/CI | Updated Github actions | bar: Winter vacation Wk 2 1
W2.3 | Documentation | Minutes and agenda | bar: Winter vacation Wk 2 1
W2.4 | Enhancement | Reordered sidebar | bar: Winter vacation Wk 2 1
13.1 | Documentation | README subheadings | bar: Week 13 23
A1.1 | New Feature | Landing page text | bar: Assessments Wk 1 9
13.2 | Documentation | Minutes and agenda | bar: Week 13 23
13.3 | New Feature | Added flashcard term to sidebar | bar: Week 13 23
13.4 | Documentation | Add firebase section to README | bar: Week 13 25
13.5 | Bug Fix | Image error | bar: Week 13 25
13.6 | Bug Fix | Headering | bar: Week 13 26
13.7 | New Feature | Added hyperlinks | bar: Week 13 26
13.8 | Enhancement | Bolding and styling | bar: Week 13 27
13.9 | Enhancement | White background for light mode | bar: Week 13 27
13.91 | Enhancement | Redesigned flashcard | bar: Week 13 27
13.92 | Enhancement | Information screen colour change | bar: Week 13 27
14.1 | New Feature | Flashcard algorithm draft 1 | bar: Week 14 30
14.2 | Enhancement | Navy icons and headers | bar: Week 14 1
14.3 | Documentation | Minutes and agenda | bar: Week 14 1
14.4 | Enhancement | Redesigned sidebar | bar: Week 14 2
14.5 | Enhancement | Resources text to black | bar: Week 14 1
14.6 | Enhancement | Capitalise headers | bar: Week 14 4
15.1 | New Feature | Issue and PR templates | bar: Week 15 9
15.2 | New Feature | Feedback Screen | bar: Week 15 9
15.3 | New Feature | Bug report and feature request templates | bar: Week 15 9
17.1 | New Feature | Sorting Algorithm test | bar: Week 17 20
15.4 | New Feature | Logo and sidebar direct to landing page | bar: Week 15 9
15.5 | New Feature | Display flashcards that are to be revised | bar: Week 15 11
15.6 | Enhancement | Flashcard dashboard redesign | bar: Week 15 11
17.2 | Enhancement | New flashcard editor | bar: Week 17 20
15.7 | Enhancement/New Feature | Loading animation and feedback styling | bar: Week 15 12
16.1 | New Feature | New dark mode | bar: Week 16 16
16.2 | New Feature | Tick and cross buttons added | bar: Week 16 13
16.3 | Bug Fix | Sign up logo error solved | bar: Week 16 13
17.3 | Enhancement | Settings update | bar: Week 17 20
17.4 | CI/CD | Streamlined actions | bar: Week 17 20
17.5 | New Feature | Nested checkbox menu | bar: Week 17 22
17.6 | CI/CD | Automatically run integration tests | bar: Week 17 23
17.7 | New Feature | Swiping functionality | bar: Week 17 25
17.8 | New Feature | Checkbox for flashcards | bar: Week 17 25
16.4 | Documentation | README table of contents | bar: Week 17 25
17.9 | Enhancement CI/CD | Integration Test update | bar: Week 17 21
17.9.1 | New Feature | Score Display | bar: Week 17 20
14.7 | Enhancement | Changed info to information | bar: Week 14 2
19.1 | New Feature | Home button navigates to flashcards dashboard | bar: Week 19 8
19.2 | New Feature | Wrong or right appears when card is swiped | bar: Week 19 7
19.3 | Documentation | Minutes | bar: Week 19 9
19.4 | New Feature | Flashcard menu for flashcard subtopics | bar: Week 19 9
19.5 | Enhancement | Add topic count for new users | bar: Week 19 9
19.6 | Enhancement | Updated spaced repeatition algorithm testing | bar: Week 19 11
19.7 | Enhancement/Bug fix | Updated score display | bar: Week 19 12
20.1 | New Feature | Loading screen | bar: Week 20 16
20.2 | New Feature | Auto-formatting | bar: Week 20 16
20.3 | New Feature | Revision plan | bar: Week 20 16
20.4 | New Feature | Comments screen | bar: Week 20 18
20.5 | CI/CD | Added dependabot | bar: Week 20 19
21.1 | New Feature | Replaced information wuth guide | bar: Week 21 21
S1.1 | Enhancement | Meets firebase security requirements | bar: Spring vacation Wk 1 1
S1.2 | New Feature | Topic colours change overtime | bar: Spring vacation Wk 1 2
S3.1 | New Feature | Added grey boxes containing intro text | bar: Spring vacation Wk 3 14
22.1 | Documentation | Minutes | bar: Week 22 17
22.2 | Bug Fix | Update old accounts | bar: Week 22 18
22.3 | New Feature | FAQ page formatting | bar: Week 22 21
22.4 | New Feature | Tick and cross tests | bar: Week 22 21
22.5 | New Feature | Colour changing background | bar: Week 22 21
23.1 | New Feature | Redirect to login page when logged out | bar: Week 23 28
24.1 | Bug Fix | Drawer widget error
24.2 | Bug Fix | Undeclared exam date in calendar |  |  | Week 1 26: 0
23.2 | New Feature | Persistent login | bar: Week 23 28
13.93 | Documentation | Add ethics to README | bar: Week 13 29
Note on DG3: Sarah Connolly: Some time in the 2 week assessment period: exams for Algorithms II, Computer Systems A and Programming Languages & Computation
Note on IC3: Sarah Connolly: Connolly:Sometime in the 3 week Assessment period: exams for Data-Driven Computer Science and Computer Systems B
Note on O4: Sarah Connolly: First client meeting First mentor meeting
Note on BJ4: Sarah Connolly: Project presentations in these 2 weeks
Note on BT4: Sarah Connolly: Computer Systems A coursework due date
Note on BX4: Minimum Viable Product Release
Note on ER4: Sarah Connolly: Deploy Beta version
Note on FR4: P2P
Note on HO4: Sarah Connolly: Deploy Final Version release
Note on HR4: Sarah Connolly: SEP Project Presentation and Demo
Note on HT4: Sarah Connolly: Interaction & Society Coursework due date